## Overview
M&M AUTO PERFORMANCE - MASTER IMPLEMENTATION ROADMAP
Project Name | M&M Auto Performance
Status | Phase 1 Planning
Launch Target | 2026 Q2
Version | 1.0 - Full Launch
PHASE | DURATION | START | END
Phase 1 MVP Launch | 2-3 weeks | Week 1 | Week 3
Phase 2 Business Automation | 2-3 weeks | Week 4 | Week 6
Phase 3 Local SEO | 2-3 weeks | Week 7 | Week 9
SUCCESS CRITERIA | TARGET | STATUS
Booking Completion Rate | >75% | Pending
Average Booking Time | <3 min | Pending
Document Verification | <2 min | Pending
System Uptime | 99.9% | Pending
Customer NPS | >70 | Pending
API Response Time | <100ms | Pending

## Phase 1 MVP
PHASE 1 MVP LAUNCH (Weeks 1-3)
COMPONENT | DESCRIPTION | PRIORITY | DAYS | OWNER
Sky Concierge Gemini | Wire API to Gemini 1.5 Flash | CRITICAL | 2 | Lead Dev
Booking Widget | Multi-step form + document upload | CRITICAL | 3 | Lead Dev
Fleet GPS Map | Real-time vehicle tracking | HIGH | 2 | Lead Dev
Admin Dashboard | View bookings, manage fleet | HIGH | 3 | Senior Dev
Database Schema | Supabase setup + migrations | CRITICAL | 1 | DBA
Authentication | Supabase Auth integration | CRITICAL | 1 | Lead Dev
Testing | Unit + E2E tests | HIGH | 2 | QA Engineer
Deployment | Vercel setup + CI/CD | CRITICAL | 1 | DevOps
TOTAL |  |  | 15

## Phase 2 Automation
PHASE 2 BUSINESS AUTOMATION (Weeks 4-6)
COMPONENT | DESCRIPTION | PRIORITY | DAYS | OWNER
Annual Returns Module | HMRC-compliant CSV/PDF | HIGH | 3 | Backend Dev
Social Media Engine | AI post scheduler 5x daily | HIGH | 2 | Frontend Dev
Asset Creator | Business card + letterhead | MEDIUM | 2 | Frontend Dev
Fleet Telematics | Driver Habit Score calc | HIGH | 3 | Data Engineer
Maintenance Alerts | Alert based on aggressive driving | MEDIUM | 2 | Backend Dev
Email Service | SendGrid integration | CRITICAL | 1 | Backend Dev
TOTAL |  |  | 13

## Phase 3 SEO
PHASE 3 LOCAL SEO DOMINANCE (Weeks 7-9)
COMPONENT | DESCRIPTION | PRIORITY | DAYS | OWNER
Local Landing Pages | St Albans, Watford, Harpenden | HIGH | 3 | Content
Schema Markup | JSON-LD CarRental + LocalBusiness | CRITICAL | 1 | SEO Dev
Google My Business | Locations + review strategy | HIGH | 2 | Marketing
ASO Optimization | App Store + Google Play | HIGH | 2 | Marketing
Backlink Strategy | Local Herts partnerships | MEDIUM | 3 | Marketing
Social Amplification | Influencer + community posts | MEDIUM | 2 | Social
TOTAL |  |  | 13

## Risk Register
RISK REGISTER & MITIGATION
RISK | DESCRIPTION | IMPACT | MITIGATION | OWNER
AI API Cost Overrun | Gemini billing spikes if traffic surges | HIGH | Implement rate limiting + budgets | Tech Lead
Supabase Free Tier Limits | Database hits row limits with growth | MEDIUM | Plan migration to paid Week 5 | DBA
Document OCR Accuracy | Misreads licenses, blocks bookings | HIGH | Use hybrid model (Vision + manual) | QA
Payment Processing Delays | Stripe not ready by Phase 1 | HIGH | Use manual payment queue | Backend
SEO Competitors React | Rivals copy local strategy | MEDIUM | Build brand loyalty via service | Marketing
Developer Availability | Key team member unavailable | HIGH | Cross-train 2 devs per component | PM

## Budget
BUDGET & RESOURCES ALLOCATION
RESOURCE | COST | PHASE | NOTES
Vercel Pro 3mo | 30 | 1-3 | Auto-deploy + analytics
Supabase Paid | 75 | 2-3 | Extra rows + support
Google Maps API | 50 | 2 | Location services
SendGrid Email | 40 | 2 | Transactional
Developer Team 12wk | 30000 | 1-3 | Salary + contractors
QA & Testing | 3000 | 1-3 | Automation + manual
Marketing & Design | 2000 | 1-3 | Assets + SMM
Miscellaneous | 1000 | 1-3 | Tools + contingency
TOTAL PROJECT COST | 36195